## Sheet1
Relative NE | Subcont | Scope | NE Region | FE Region | Time | Execution Date | Weekly | CR Level | Dependency Qty | Site Dependency | Impact Data Source | RFC Number | CR Number | Current Status | Originator | Ticket status | MOP File Name | Email File Name | CTO List
090473_092252MD296 | Tritama | MW REROUTE | JABO 1 | JABO 1 | 13.00 - 17.00 | 2022-01-21 | W03 | R3 | 0 | - | E2E Conet | - | CR-20220119-00144 | Analyze L1 | Aktortifan Ridno Prabu Pratama | 2nd use | HW_WT_TX_Microwave Link Reroute JABO 1 Area _W03 | Need Approval CR Activity Plan Week 03 (21 January - 23 January) for the MW activity (JABO-1)
094420_096112MD286 | CCSI | MW REROUTE | JABO 3 | JABO 3 | 13.00 - 17.00 | 2022-01-21 | W03 | R3 | 0 | - | E2E Conet | - | CR-20220118-00070 | Analyze L1 | Aktortifan Ridno Prabu Pratama | 2nd use | HW_WT_TX_Microwave Link Reroute JABO 3 Area _W03 | Need to Confirm CR MW 21 January - 23 January for the MW activities. (JABO-3)
104019_100810MU003 | Aswinda | Software Upgrade | JABO 2 | JABO 2 | 00.00 - 04.00 | 2022-01-21 | W03 | R3 | 4 | 603657,103986,603707,104019 | E2E Conet | - | CR-20220120-00188 | Analyze L1 | Aktortifan Ridno Prabu Pratama | 1st use | HW_WT_TX_Software Upgrade JABO 2 Area _W03 | HW_WT_TX_Software Upgrade JABO 2 Area _W03
102223_101645MU003 | Aswinda | Software Upgrade | JABO 2 | JABO 2 | 00.00 - 04.00 | 2022-01-21 | W03 | R3 | 3 | 103747,102934,102223 | E2E Conet | - | CR-20220120-00188 | Analyze L1 | Aktortifan Ridno Prabu Pratama | 1st use | HW_WT_TX_Software Upgrade JABO 2 Area _W03 | HW_WT_TX_Software Upgrade JABO 2 Area _W03
280040_280002MU003 | Aswinda | Software Upgrade | JABO 3 | JABO 3 | 00.00 - 04.00 | 2022-01-21 | W03 | R3 | 7 | 281513,280787,280654,280715,281501,280145,280040 | E2E Conet | - | CR-20220120-00194 | Analyze L1 | Aktortifan Ridno Prabu Pratama | 1st use | HW_WT_TX_Software Upgrade JABO 3 Area _W03 | Need to Confirm CR MW 21 January - 23 January for the MW activities. (JABO-3)
280456_100315MU003 | Aswinda | Software Upgrade | JABO 3 | JABO 3 | 00.00 - 04.00 | 2022-01-21 | W03 | R3 | 6 | 281490,094639,280953,281391,280969,280456 | E2E Conet | - | CR-20220120-00194 | Analyze L1 | Aktortifan Ridno Prabu Pratama | 1st use | HW_WT_TX_Software Upgrade JABO 3 Area _W03 | Need to Confirm CR MW 21 January - 23 January for the MW activities. (JABO-3)
280055_280002MU003 | Aswinda | Software Upgrade | JABO 3 | JABO 3 | 00.00 - 04.00 | 2022-01-21 | W03 | R3 | 6 | 102006,281464,280801,280071,280718,280055 | E2E Conet | - | CR-20220120-00194 | Analyze L1 | Aktortifan Ridno Prabu Pratama | 1st use | HW_WT_TX_Software Upgrade JABO 3 Area _W03 | Need to Confirm CR MW 21 January - 23 January for the MW activities. (JABO-3)
100423_100418MU001 | Aswinda | Software Upgrade | JABO 2 | JABO 2 | 00.00 - 04.00 | 2022-01-21 | W03 | R3 | 5 | 603626,603625,100620,604307,100423 | E2E Conet | - | CR-20220120-00188 | Analyze L1 | Aktortifan Ridno Prabu Pratama | 1st use | HW_WT_TX_Software Upgrade JABO 2 Area _W03 | HW_WT_TX_Software Upgrade JABO 2 Area _W03
100410_100385MU003 | Aswinda | Software Upgrade | JABO 2 | JABO 2 | 00.00 - 04.00 | 2022-01-21 | W03 | R3 | 5 | 602350,104013,103998,604167,100410 | E2E Conet | - | CR-20220120-00188 | Analyze L1 | Aktortifan Ridno Prabu Pratama | 1st use | HW_WT_TX_Software Upgrade JABO 2 Area _W03 | HW_WT_TX_Software Upgrade JABO 2 Area _W03
096674_590214MU003 | Aswinda | Software Upgrade | JABO 1 | JABO 1 | 00.00 - 04.00 | 2022-01-21 | W03 | R3 | 6 | 094586,096969,090389,590520,090381,096674 | E2E Conet | - | CR-20220120-00181 | Analyze L1 | Aktortifan Ridno Prabu Pratama | 1st use | HW_WT_TX_Software Upgrade JABO 1 Area _W03 | Need Approval CR Activity Plan Week 03 (21 January - 23 January) for the MW activity (JABO-1)
100200_107003MD286 | INTISEL | MW REROUTE | JABO 2 | JABO 2 | 13.00 - 17.00 | 2022-01-21 | W03 | R3 | 0 | - | E2E Conet | - | CR-20220118-00067 | Analyze L1 | Aktortifan Ridno Prabu Pratama | 2nd use | HW_WT_TX_Microwave Link Reroute JABO 2 Area _W03 | Need the CR approval MW Plan W03 (21 January 2022 23 January 2022) for the MW activity under_Jabo2 (JABO-2)
100803_100426MDP282 | DSB | MW REROUTE | JABO 2 | JABO 2 | 13.00 - 17.00 | 2022-01-21 | W03 | R3 | 0 | - | E2E Conet | - | CR-20220118-00067 | Analyze L1 | Aktortifan Ridno Prabu Pratama | 2nd use | HW_WT_TX_Microwave Link Reroute JABO 2 Area _W03 | Need the CR approval MW Plan W03 (21 January 2022 23 January 2022) for the MW activity under_Jabo2 (JABO-2)
090478_092242MD013 | ADW | MW REROUTE | JABO 1 | JABO 1 | 13.00 - 17.00 | 2022-01-21 | W03 | R3 | 0 | - | E2E Conet | - | CR-20220119-00144 | Analyze L1 | Aktortifan Ridno Prabu Pratama | 2nd use | HW_WT_TX_Microwave Link Reroute JABO 1 Area _W03 | Need Approval CR Activity Plan Week 03 (21 January - 23 January) for the MW activity (JABO-1)
100610_100314MRN322 | DSB | MW REROUTE | JABO 3 | JABO 3 | 13.00 - 17.00 | 2022-01-21 | W03 | R3 | 10 | 103800,281550,103875,281628,103790,095664,100875,282020,281148,100610 | E2E Conet | - | CR-20220118-00070 | Analyze L1 | Aktortifan Ridno Prabu Pratama | 2nd use | HW_WT_TX_Microwave Link Reroute JABO 3 Area _W03 | Need to Confirm CR MW 21 January - 23 January for the MW activities. (JABO-3)
100826_100798MR230 | ADW | MW REROUTE | JABO 2 | JABO 2 | 13.00 - 17.00 | 2022-01-21 | W03 | R3 | 6 | 104027,100816,602950,603751,603743,100826 | E2E Conet | - | CR-20220118-00067 | Analyze L1 | Aktortifan Ridno Prabu Pratama | 2nd use | HW_WT_TX_Microwave Link Reroute JABO 2 Area _W03 | Need the CR approval MW Plan W03 (21 January 2022 23 January 2022) for the MW activity under_Jabo2 (JABO-2)
101874_100803MRN258 | MPJ | MW REROUTE | JABO 2 | JABO 2 | 13.00 - 17.00 | 2022-01-21 | W03 | R3 | 4 | 103760,602863,603613,101874 | E2E Conet | - | CR-20220118-00067 | Analyze L1 | Aktortifan Ridno Prabu Pratama | 2nd use | HW_WT_TX_Microwave Link Reroute JABO 2 Area _W03 | Need the CR approval MW Plan W03 (21 January 2022 23 January 2022) for the MW activity under_Jabo2 (JABO-2)
104023_100274MRU230 | DSB | MW REROUTE | JABO 2 | JABO 2 | 13.00 - 17.00 | 2022-01-21 | W03 | R3 | 4 | 603752,602931,603669,104023 | E2E Conet | - | CR-20220118-00067 | Analyze L1 | Aktortifan Ridno Prabu Pratama | 2nd use | HW_WT_TX_Microwave Link Reroute JABO 2 Area _W03 | Need the CR approval MW Plan W03 (21 January 2022 23 January 2022) for the MW activity under_Jabo2 (JABO-2)
100171_100175MD017 | INTISEL | MW REROUTE | JABO 1 | JABO 1 | 13.00 - 17.00 | 2022-01-21 | W03 | R3 | 0 | - | E2E Conet | - | CR-20220119-00144 | Analyze L1 | Aktortifan Ridno Prabu Pratama | 2nd use | HW_WT_TX_Microwave Link Reroute JABO 1 Area _W03 | Need Approval CR Activity Plan Week 03 (21 January - 23 January) for the MW activity (JABO-1)
105082_100207MDR283 | NEXWAVE | MW REROUTE | JABO 2 | JABO 2 | 13.00 - 17.00 | 2022-01-21 | W03 | R3 | 0 | - | E2E Conet | - | CR-20220118-00067 | Analyze L1 | Aktortifan Ridno Prabu Pratama | 2nd use | HW_WT_TX_Microwave Link Reroute JABO 2 Area _W03 | Need the CR approval MW Plan W03 (21 January 2022 23 January 2022) for the MW activity under_Jabo2 (JABO-2)
602312_101020MR230 | DSB | MW REROUTE | JABO 2 | JABO 2 | 13.00 - 17.00 | 2022-01-21 | W03 | R3 | 1 | 602312 | E2E Conet | - | CR-20220118-00067 | Analyze L1 | Aktortifan Ridno Prabu Pratama | 2nd use | HW_WT_TX_Microwave Link Reroute JABO 2 Area _W03 | Need the CR approval MW Plan W03 (21 January 2022 23 January 2022) for the MW activity under_Jabo2 (JABO-2)
603350_100253MRN323 | TSP | MW REROUTE | JABO 2 | JABO 2 | 13.00 - 17.00 | 2022-01-21 | W03 | R3 | 1 | 603350 | E2E Conet | - | CR-20220118-00067 | Analyze L1 | Aktortifan Ridno Prabu Pratama | 2nd use | HW_WT_TX_Microwave Link Reroute JABO 2 Area _W03 | Need the CR approval MW Plan W03 (21 January 2022 23 January 2022) for the MW activity under_Jabo2 (JABO-2)