## Sheet1
Relative NE | Subcont | Scope | NE Region | FE Region | Time | Execution Date | Weekly | CR Level | Dependency Qty | Site Dependency | Impact Data Source | RFC Number | CR Number | Current Status | Originator | Ticket status | MOP File Name | Email File Name | NE Area | ATF Number
603350_100253MRN323 | Deka | Cutover | JABO 2 | JABO 2 | 13.00 - 17.00 | 2022-02-01 | W05 | R3 | 1 | 603350 | E2E Conet | - |  |  |  |  | HW_Wireless_Cutover_under 603350_100253MRN323_JABO 2 Midday (1 Feb) | Need the CR approval MW Plan W05 (1 February 2022 6 February 2022) for the MW activity under_Jabo2 (JABO2) | KOTA BOGOR | No Need
603350_100607MDR323 | TSP | MW Reroute | JABO 2 | JABO 2 | 13.00 - 17.00 | 2022-02-01 | W05 | R3 | 0 | - | E2E Conet | - |  |  |  |  | HW_TX_Microwave Link Reroute JABO 2 Area _W05 (1 Feb) | Need the CR approval MW Plan W05 (1 February 2022 6 February 2022) for the MW activity under_Jabo2 (JABO2) | KOTA BOGOR | NOK
603350_100253MRN323 | TSP | MW Reroute | JABO 2 | JABO 2 | 13.00 - 17.00 | 2022-02-01 | W05 | R3 | 1 | 603350 | E2E Conet | - |  |  |  |  | HW_TX_Microwave Link Reroute JABO 2 Area _W05 (1 Feb) | Need the CR approval MW Plan W05 (1 February 2022 6 February 2022) for the MW activity under_Jabo2 (JABO2) | KOTA BOGOR | NOK
601005_104126MDR003 | INTISEL | MW Reroute | JABO 2 | JABO 2 | 13.00 - 17.00 | 2022-02-01 | W05 | R3 | 0 | - | E2E Conet | - |  |  |  |  | HW_TX_Microwave Link Reroute JABO 2 Area _W05 (1 Feb) | Need the CR approval MW Plan W05 (1 February 2022 6 February 2022) for the MW activity under_Jabo2 (JABO2) | KAB. BOGOR | NOK
280143_280061MDR308 | INTISEL | MW Reroute | JABO 3 | JABO 3 | 13.00 - 17.00 | 2022-02-01 | W05 | R3 | 0 | - | E2E Conet | - |  |  |  |  | HW_TX_Microwave Link Reroute JABO 3 Area _W05 (1 Feb) | Need to Confirm CR MW 1 February - 6 February for the MW activities (JABO3). | KOTA SERANG | NOK
094288_094280MD013 | INTISEL | MW Reroute | JABO 1 | JABO 1 | 13.00 - 17.00 | 2022-02-01 | W05 | R3 | 0 | - | E2E Conet | - |  |  |  |  | HW_TX_Microwave Link Reroute JABO 1 Area _W05 (1 Feb) | Need Approval CR Activity Plan Week 05 (31 Jan - 6 Feb) (JABO1)for the MW activity | JAKARTA SELATAN | A7998/NSM CSM SSE JB WJ CJ EJ CEK BLM SSL NSL/IN-DOP/11-2020
602312_101020MR230 | DSB | MW Reroute | JABO 2 | JABO 2 | 13.00 - 17.00 | 2022-02-01 | W05 | R3 | 1 | 602312 | E2E Conet | - |  |  |  |  | HW_TX_Microwave Link Reroute JABO 2 Area _W05 (1 Feb) | Need the CR approval MW Plan W05 (1 February 2022 6 February 2022) for the MW activity under_Jabo2 (JABO2) | KOTA BOGOR | NOK
603350_100253MRN323 | Deka | Cutover | JABO 2 | JABO 2 | 13.00 - 17.00 | 2022-02-02 | W05 | R3 | 1 | 603350 | E2E Conet | - |  |  |  |  | HW_Wireless_Cutover_under 603350_100253MRN323_JABO 2 Midday (2 Feb) | Need the CR approval MW Plan W05 (1 February 2022 6 February 2022) for the MW activity under_Jabo2 (JABO2) | KOTA BOGOR | No Need
603350_100607MDR323 | TSP | MW Reroute | JABO 2 | JABO 2 | 13.00 - 17.00 | 2022-02-02 | W05 | R3 | 0 | - | E2E Conet | - |  |  |  |  | HW_TX_Microwave Link Reroute JABO 2 Area _W05 (2 Feb) | Need the CR approval MW Plan W05 (1 February 2022 6 February 2022) for the MW activity under_Jabo2 (JABO2) | KOTA BOGOR | NOK
603350_100253MRN323 | TSP | MW Reroute | JABO 2 | JABO 2 | 13.00 - 17.00 | 2022-02-02 | W05 | R3 | 1 | 603350 | E2E Conet | - |  |  |  |  | HW_TX_Microwave Link Reroute JABO 2 Area _W05 (2 Feb) | Need the CR approval MW Plan W05 (1 February 2022 6 February 2022) for the MW activity under_Jabo2 (JABO2) | KOTA BOGOR | NOK
601005_104126MDR003 | INTISEL | MW Reroute | JABO 2 | JABO 2 | 13.00 - 17.00 | 2022-02-02 | W05 | R3 | 0 | - | E2E Conet | - |  |  |  |  | HW_TX_Microwave Link Reroute JABO 2 Area _W05 (2 Feb) | Need the CR approval MW Plan W05 (1 February 2022 6 February 2022) for the MW activity under_Jabo2 (JABO2) | KAB. BOGOR | NOK
280143_280061MDR308 | INTISEL | MW Reroute | JABO 3 | JABO 3 | 13.00 - 17.00 | 2022-02-02 | W05 | R3 | 0 | - | E2E Conet | - |  |  |  |  | HW_TX_Microwave Link Reroute JABO 3 Area _W05 (2 Feb) | Need to Confirm CR MW 1 February - 6 February for the MW activities (JABO3). | KOTA SERANG | NOK
094288_094280MD013 | INTISEL | MW Reroute | JABO 1 | JABO 1 | 13.00 - 17.00 | 2022-02-02 | W05 | R3 | 0 | - | E2E Conet | - |  |  |  |  | HW_TX_Microwave Link Reroute JABO 1 Area _W05 (2 Feb) | Need Approval CR Activity Plan Week 05 (31 Jan - 6 Feb) (JABO1)for the MW activity | JAKARTA SELATAN | A7998/NSM CSM SSE JB WJ CJ EJ CEK BLM SSL NSL/IN-DOP/11-2020
602312_101020MR230 | DSB | MW Reroute | JABO 2 | JABO 2 | 13.00 - 17.00 | 2022-02-02 | W05 | R3 | 1 | 602312 | E2E Conet | - |  |  |  |  | HW_TX_Microwave Link Reroute JABO 2 Area _W05 (2 Feb) | Need the CR approval MW Plan W05 (1 February 2022 6 February 2022) for the MW activity under_Jabo2 (JABO2) | KOTA BOGOR | NOK
280143_280007MRN308 | INTISEL | MW Reroute | JABO 3 | JABO 3 | 13.00 - 17.00 | 2022-02-01 | W05 | R3 | 2 | 281673,280143 | E2E Conet | - |  |  |  |  | HW_TX_Microwave Link Reroute JABO 3 Area _W05 (1 Feb) | Need to Confirm CR MW 1 February - 6 February for the MW activities (JABO3). | KOTA SERANG | NOK
280143_280007MRN308 | INTISEL | MW Reroute | JABO 3 | JABO 3 | 13.00 - 17.00 | 2022-02-02 | W05 | R3 | 2 | 281673,280143 | E2E Conet | - |  |  |  |  | HW_TX_Microwave Link Reroute JABO 3 Area _W05 (2 Feb) | Need to Confirm CR MW 1 February - 6 February for the MW activities (JABO3). | KOTA SERANG | NOK
Note on D1: Aktortifan Ridno Prabu Pratama:
Note on E1: Aktortifan Ridno Prabu Pratama:
Note on I1: Aktortifan Ridno Prabu Pratama:
Note on J1: =IFERROR(IF(SEARCH("md",A3),0), IFNA(VLOOKUP(LEFT(A3,13),Conet!B:Q,16,FALSE), VLOOKUP(A3,'Additional Sites'!A:F,6,FALSE)))
Note on K1: Aktortifan Ridno Prabu Pratama: =IFERROR(IF(SEARCH("md",A3),"-"), IFNA(VLOOKUP(LEFT(A3,13),Conet!B:P,15,FALSE), VLOOKUP(A3,'Additional Sites'!A:G,7,FALSE)))